SRM INSTITUTE OF SCIENCE AND TECHNOLOGY

Department of Robotics and Automation Engineering

AUTONOMOUS ELECTRIC CAMPUS BUGGY Phase 1 — Software-in-the-Loop (SITL) Simulation Complete 10-Day Master Implementation Plan

| Parameter | Value |
| --- | --- |
| Platform | Ubuntu 22.04 LTS + ROS 2 Humble + Gazebo Classic 11 |
| Language | Python 3 (nodes) ¦ Bash (scripts) ¦ SDF/XACRO (models) |
| IDE | Visual Studio Code with ROS extension |
| Sprint Duration | 10 Days — 6-Person Team |
| Sprint Goal | One-command autonomous SITL prototype with full traceability |
| Vehicle Base | Pre-existing Golf Cart URDF from GitHub (surgically modified) |
| Max Speed | 15 km/h (4.17 m/s) |
| World Size | 50 m x 50 m mini-campus with 3 destinations + HUB node |
| Document Version | v1.0 ¦ March 2026 ¦ SRM Autonomous Buggy Team |

STRICTLY CONFIDENTIAL — INTERNAL USE ONLY

# 1. Executive Summary

This document is the unified, synthesised, and fully executable Phase 1 Software-in-the-Loop (SITL) Master Implementation Plan for the SRM Autonomous Electric Campus Buggy project. It has been created by consolidating every team member's ideas, the two uploaded implementation plans, and the GitHub research collected by the team, into a single authoritative plan that leaves no ambiguity, no scope creep, and no loopholes.

The project's mission is straightforward: take the autonomous buggy that currently exists only as a document and a physical vehicle nobody has touched, and build the first running, observable, demonstrable version of it — entirely inside a computer. Not a generic robotics tutorial. Not someone else's demo. Your specific vehicle, your specific sensors, your specific safety rules, and your specific campus roads, all converted into working software.

## 1.1 What the Final System Does

EXPECTED OUTCOME: You launch one command. A Gazebo window opens showing the 3D campus world with the buggy sitting at START. A terminal asks: 'Select Destination: (A) Main Gate (B) Library Block (C) Admin Block'. You type B and press Enter. The system computes the shortest path using Dijkstra's algorithm, prints 'Shortest Path: START → HUB → Library Block (40m)'. The buggy begins driving at 15 km/h. It detects an obstacle at 1.5m, stops, waits, resumes. It reaches Library Block and announces arrival. It then asks for the next destination. This runs forever, reliably, without crashing, without human intervention.

## 1.2 What This Plan Is NOT

- NOT a Nav2 costmap / DWB planner implementation — too complex, out of scope

- NOT SLAM (slam_toolbox) — mapping is hardcoded, no dynamic map building

- NOT YOLO or any computer vision — crowd detection is LiDAR-based threshold

- NOT Gazebo Fortress or Ignition — Classic 11 only, stable binaries exist

- NOT custom 3D modelling — no Blender, no SolidWorks, no CAD from scratch

- NOT Ackermann steering — differential drive only, matches golf cart kinematics

## 1.3 Why This Approach is Correct

Every design decision in this plan is traced to a specific section in the SRM Implementation Plan documents. The 1.5m obstacle threshold is Section 5.1. The 15 km/h speed limit is Section 2.2. The ultrasonic perimeter at 30 cm is Section 11.1. The defence-in-depth architecture is Section 11.1. This traceability is what makes this a legitimate Phase 1 engineering deliverable and not a student prototype.

# 2. Technology Stack — Fixed, No Deviations

The following technology choices are non-negotiable. Every tool has been selected for binary availability, community support, and known compatibility with the team's hardware.

## 2.1 Core Platform

| Component | Choice | Reason |
| --- | --- | --- |
| Operating System | Ubuntu 22.04 LTS | ROS 2 Humble binary apt packages exist only for 22.04. Any other Ubuntu version requires painful source compilation. |
| ROS Middleware | ROS 2 Humble Hawksbill | LTS release, massive community, stable Gazebo bridge, 5-year support window. |
| Simulation Engine | Gazebo Classic 11 | Mature, well-documented, gazebo_ros_pkgs bridge is battle-tested. NOT Fortress — bridge complexity doubles with Fortress. |
| Development IDE | VS Code + ROS Extension | Syntax highlighting, integrated terminal, ROS topic/node explorer via extension. |
| Build System | colcon + ament_python | Standard ROS 2 Python build tool. Do not use catkin or cmake directly. |
| Node Language | Python 3.10 | All ROS 2 perception/control nodes are Python. Fast to write, easy to debug, sufficient performance for simulation. |
| Terminal Multiplexer | tmux | Four-pane live dashboard during demo. apt install tmux. |
| Version Control | Git + GitHub | All code pushed daily to team GitHub repository. |

## 2.2 Key ROS 2 Packages to Install

Run this single command on Day 1 to install all required packages:

sudo apt update

sudo apt install -y \

ros-humble-desktop \

ros-humble-gazebo-ros-pkgs \

ros-humble-gazebo-ros2-control \

ros-humble-robot-state-publisher \

ros-humble-joint-state-publisher \

ros-humble-rviz2 \

ros-humble-xacro \

ros-humble-nav-msgs \

ros-humble-sensor-msgs \

ros-humble-geometry-msgs \

ros-humble-std-msgs \

ros-humble-tf2-ros \

ros-humble-tf2-tools \

ros-humble-rqt \

ros-humble-rqt-graph \

ros-humble-rqt-image-view \

python3-colcon-common-extensions \

python3-rosdep \

tmux

## 2.3 GitHub Repository Strategy

PRIMARY VEHICLE BASE: Search GitHub on Day 1 — query: 'golf cart urdf ros2 gazebo diff_drive'. The Andino robot (https://github.com/Ekumen-OS/andino) is a confirmed working ROS 2 Humble differential drive robot with Gazebo Classic support. The self-driving golf cart project (https://github.com/sigmaai/self-driving-golf-cart) provides visual reference. The gazebo_ros2_control test cart (https://github.com/ros-controls/gazebo_ros2_control/blob/master/gazebo_ros2_control_demos/urdf/test_cart_effort.xacro.urdf) is a confirmed working XACRO. FALLBACK: sudo apt install ros-humble-husky-description — Clearpath Husky URDF, zero configuration needed.

## 2.4 Your Team's GitHub Repository Structure

Create one repository named srm-autonomous-buggy and structure it as follows:

| Folder / File | Contents |
| --- | --- |
| /buggy_description | URDF/XACRO files, meshes, sensor plugin configs — the virtual vehicle |
| /buggy_bringup | All launch files, world files, RViz2 config files |
| /buggy_brain | All Python ROS 2 nodes: perception, state machine, navigation, visualization |
| /docs | Your original PDF implementation plan, traceability matrix, screenshots |
| README.md | How-to-run instructions, traceability table, topic list, node list |
| .gitignore | Exclude: build/, install/, log/, __pycache__/, *.pyc |
| run_demo.sh | Single-command launcher script — the final deliverable entry point |

# 3. Virtual Vehicle Model — URDF Construction

The buggy is defined in URDF (Unified Robot Description Format) using XACRO macros. You are not building this from scratch. You are cloning a working base and surgically adding your five sensors to it.

## 3.1 Base Model Selection — Day 1 Priority

RULE: If a working golf cart URDF with diff_drive plugin and /cmd_vel subscriber is not found on GitHub within 90 minutes of searching on Day 1, immediately fall back to Clearpath Husky. Install with: sudo apt install ros-humble-husky-description. A working vehicle is worth infinitely more than a visually accurate one for a Phase 1 deliverable. You can rename it 'SRM Campus Buggy' in the URDF and nobody will care — what matters is it moves.

## 3.2 Sensor Link Placements — Exact Positions

Add the following eight sensor links to the cloned XACRO file as fixed joints attached to base_link. Do not modify any existing joints. Only add:

| Sensor Link Name | XYZ Offset (metres) | Description |
| --- | --- | --- |
| lidar_link | 0.0 0.0 1.85 | Roof centre — Livox Mid-360 LiDAR proxy |
| camera_link | 1.2 0.0 1.20 | Front face at eye height — RealSense D435i proxy |
| imu_link | 0.0 0.0 0.50 | Vehicle centroid — BNO055 IMU proxy |
| gps_link | -0.5 0.0 1.60 | Rear top — U-blox GPS proxy |
| ultrasonic_front_link | 1.5 0.0 0.30 | Front corner — HC-SR04 proxy |
| ultrasonic_rear_link | -1.5 0.0 0.30 | Rear corner — HC-SR04 proxy |
| ultrasonic_left_link | 0.0 0.8 0.30 | Left side — HC-SR04 proxy |
| ultrasonic_right_link | 0.0 -0.8 0.30 | Right side — HC-SR04 proxy |

## 3.3 XACRO Sensor Link Code Template

For each sensor, add this pattern to the base XACRO file after the existing base_link definition:

<link name="lidar_link">

<visual><geometry><cylinder radius="0.05" length="0.08"/></geometry></visual>

<collision><geometry><cylinder radius="0.05" length="0.08"/></geometry></collision>

<inertial><mass value="0.1"/><inertia ixx="0.001" iyy="0.001" izz="0.001"/></inertial>

</link>

<joint name="lidar_joint" type="fixed">

<parent link="base_link"/>

<child link="lidar_link"/>

<origin xyz="0.0 0.0 1.85" rpy="0 0 0"/>

</joint>

# 4. Sensor Plugin Configuration — All Five Sensors

Every sensor uses the gazebo_ros_pkgs plugin library. These are added inside <gazebo reference="sensor_link_name"> blocks in the XACRO file. All topics are real ROS 2 message streams — not mocks, not hardcoded data.

## 4.1 LiDAR — Livox Mid-360 Proxy

| Parameter | Value |
| --- | --- |
| Gazebo Plugin | libgazebo_ros_ray_sensor.so |
| ROS 2 Topic | /scan |
| Message Type | sensor_msgs/LaserScan |
| Horizontal Scan | 360 degrees, 360 samples (NOT 200,000 — kills GPU) |
| Range Min/Max | 0.1m — 30.0m |
| Update Rate | 10 Hz |
| Plan Reference | Section 3.2, Section 4.1 |
| Verification | ros2 topic echo /scan → ranges[] must show real float values, not all zeros or inf |

<gazebo reference="lidar_link">

<sensor type="ray" name="lidar_sensor">

<pose>0 0 0 0 0 0</pose>

<visualize>true</visualize>

<update_rate>10</update_rate>

<ray>

<scan><horizontal><samples>360</samples><min_angle>-3.14159</min_angle><max_angle>3.14159</max_angle></horizontal></scan>

<range><min>0.1</min><max>30.0</max><resolution>0.01</resolution></range>

</ray>

<plugin name="lidar_plugin" filename="libgazebo_ros_ray_sensor.so">

<ros><namespace>/</namespace><remapping>~/out:=scan</remapping></ros>

<output_type>sensor_msgs/LaserScan</output_type>

<frame_name>lidar_link</frame_name>

</plugin>

</sensor>

</gazebo>

## 4.2 Camera — Intel RealSense D435i Proxy

| Parameter | Value |
| --- | --- |
| Gazebo Plugin | libgazebo_ros_camera.so |
| ROS 2 Topic | /camera/image_raw |
| Resolution | 640 x 480 pixels |
| Frame Rate | 30 Hz |
| Field of View | 1.047 radians (60 degrees) |
| Plan Reference | Section 3.2, Section 4.2 |
| Verification | ros2 run rqt_image_view rqt_image_view → must show live road image |

## 4.3 IMU — BNO055 Proxy

| Parameter | Value |
| --- | --- |
| Gazebo Plugin | libgazebo_ros_imu_sensor.so |
| ROS 2 Topic | /imu/data |
| Message Type | sensor_msgs/Imu |
| Update Rate | 100 Hz |
| Plan Reference | Section 3.2, Section 4.3 |

## 4.4 GPS — U-blox Proxy

| Parameter | Value |
| --- | --- |
| Gazebo Plugin | libgazebo_ros_gps_sensor.so |
| ROS 2 Topic | /gps/fix |
| Message Type | sensor_msgs/NavSatFix |
| Plan Reference | Section 3.2, Section 4.4 |

## 4.5 Ultrasonic Sensors — HC-SR04 Proxy (x4)

| Parameter | Value |
| --- | --- |
| Gazebo Plugin | libgazebo_ros_ray_sensor.so (narrow beam) |
| Topics | /ultrasonic/front, /ultrasonic/rear, /ultrasonic/left, /ultrasonic/right |
| Message Type | sensor_msgs/LaserScan |
| Beam Width | 3 horizontal samples, ±3 degree spread |
| Max Range | 2.0 metres |
| Stop Threshold | 0.30 metres (Section 11.1) |
| Plan Reference | Section 11.1 — Defence-in-Depth Architecture |
| Verification | ros2 topic echo /ultrasonic/front → single range value updating at 10Hz |

## 4.6 Complete Topic Registry

| ROS 2 Topic | Message Type | Source / Consumer |
| --- | --- | --- |
| /scan | sensor_msgs/LaserScan | Gazebo LiDAR → obstacle_detector_node |
| /camera/image_raw | sensor_msgs/Image | Gazebo Camera → RViz2 display |
| /imu/data | sensor_msgs/Imu | Gazebo IMU → (Phase 2 fusion) |
| /gps/fix | sensor_msgs/NavSatFix | Gazebo GPS → terminal dashboard |
| /ultrasonic/front | sensor_msgs/LaserScan | Gazebo Ultrasonic → ultrasonic_monitor_node |
| /ultrasonic/rear | sensor_msgs/LaserScan | Gazebo Ultrasonic → ultrasonic_monitor_node |
| /ultrasonic/left | sensor_msgs/LaserScan | Gazebo Ultrasonic → ultrasonic_monitor_node |
| /ultrasonic/right | sensor_msgs/LaserScan | Gazebo Ultrasonic → ultrasonic_monitor_node |
| /odom | nav_msgs/Odometry | Diff Drive Plugin → waypoint_follower_node |
| /cmd_vel | geometry_msgs/Twist | speed_controller_node → Diff Drive Plugin |
| /obstacle_detected | std_msgs/Bool | obstacle_detector_node → state_machine_node |
| /obstacle_direction | std_msgs/Float32 | obstacle_detector_node → visualizer_node |
| /ultrasonic_alert | std_msgs/Bool | ultrasonic_monitor_node → state_machine_node |
| /crowd_detected | std_msgs/Bool | crowd_detector_node → state_machine_node |
| /buggy_state | std_msgs/String | state_machine_node → speed_controller_node |
| /planned_path | nav_msgs/Path | path_planner_node → waypoint_follower_node + RViz2 |
| /navigation_command | std_msgs/String | path_planner_node → state_machine_node |
| /visualization_markers | visualization_msgs/MarkerArray | visualizer_node → RViz2 |

# 5. Gazebo Campus World Design

The simulated world is a 50x50 metre mini-campus with a road network that matches the hardcoded Dijkstra graph. The physical geometry and the navigation graph must be consistent — if the graph says HUB is at (0,0), the road intersection in Gazebo must also be at (0,0).

## 5.1 Road Network and Named Nodes

| Node Name | Coordinates (x, y) in Gazebo World |
| --- | --- |
| START (Buggy Spawn) | (-20.0, 0.0) |
| HUB (Central Intersection) | (0.0, 0.0) |
| A — Main Gate | (-20.0, 0.0) — same as START for demo simplicity |
| B — Library Block | (20.0, 0.0) |
| C — Admin Block | (0.0, 20.0) |

## 5.2 Campus World SDF Elements

- Ground plane with grey tarmac texture

- Straight road: START (-20,0) to HUB (0,0) — 20m, 4m wide grey box, z=0.01

- Straight road: HUB (0,0) to Library (20,0) — 20m, 4m wide grey box

- Straight road: HUB (0,0) to Admin (0,20) — 20m, 4m wide grey box

- Building walls: 0.3m thick, 3m tall boxes along road edges

- Destination markers: tall coloured cylinders at B and C for visual reference

- 3 obstacle boxes: moveable boxes placed on roads for testing — can be dragged in Gazebo GUI

- Sun directional light for clear rendering

## 5.3 SDF World File Location

Save the world file at: ~/srm_buggy_ws/src/buggy_bringup/worlds/srm_campus.world

The launch file will reference this world. Gazebo Classic reads SDF natively. Your URDF/XACRO robot is spawned separately by the spawn_entity.py node.

## 5.4 Obstacle Placement Strategy

Place three obstacle boxes at these positions for reliable demo testing:

| Obstacle | Position (x, y) |
| --- | --- |
| obstacle_box_1 | (-10.0, 0.0) |
| obstacle_box_2 | (10.0, 0.0) |
| crowd_cluster | (5.0, 0.0) — 6 small boxes in semicircle |

# 6. Software Architecture — All ROS 2 Nodes

The autonomous stack consists of seven Python ROS 2 nodes. Each is a separate file in the buggy_brain package. All nodes are registered in setup.py entry_points so they can be launched by name.

PACKAGE STRUCTURE: ~/srm_buggy_ws/src/buggy_brain/buggy_brain/ map_graph.py (pure Python module — no ROS, just the graph + Dijkstra) path_planner_node.py (terminal input + path computation + /planned_path publisher) waypoint_follower.py (odometry reader + P-controller + /cmd_vel publisher) obstacle_detector.py (/scan reader + /obstacle_detected + /obstacle_direction) ultrasonic_monitor.py(4x ultrasonic readers + /ultrasonic_alert) state_machine.py (master FSM — reads all alerts, publishes /buggy_state) speed_controller.py (/buggy_state reader + /cmd_vel publisher with speed logic) crowd_detector.py (LiDAR ray-count threshold → /crowd_detected) demo_visualizer.py (MarkerArray publisher for RViz2 waypoints + path + obstacle dot)

## 6.1 map_graph.py — Campus Road Graph + Dijkstra

This is a pure Python module. No ROS imports. Defines the campus as a graph and implements shortest-path computation.

NODES = {

'START': (-20.0, 0.0),

'HUB':   (0.0, 0.0),

'A':     (-20.0, 0.0),   # Main Gate (same as start for demo)

'B':     (20.0, 0.0),    # Library Block

'C':     (0.0, 20.0),    # Admin Block

}

EDGES = {

'START': [('HUB', 20.0)],

'HUB':   [('START', 20.0), ('B', 20.0), ('C', 20.0)],

'B':     [('HUB', 20.0)],

'C':     [('HUB', 20.0)],

}

import heapq

def find_shortest_path(graph, start, goal):

pq = [(0, start)]

distances = {n: float('inf') for n in graph}

distances[start] = 0

previous = {n: None for n in graph}

while pq:

cost, node = heapq.heappop(pq)

if node == goal: break

for neighbor, weight in graph[node]:

new_cost = cost + weight

if new_cost < distances[neighbor]:

distances[neighbor] = new_cost

previous[neighbor] = node

heapq.heappush(pq, (new_cost, neighbor))

path = []

node = goal

while node is not None:

path.append(node)

node = previous[node]

return list(reversed(path))

CRITICAL TESTING STEP: Before integrating with ROS, run python3 map_graph.py standalone and verify:

- find_shortest_path(EDGES, 'START', 'B') → ['START', 'HUB', 'B']

- find_shortest_path(EDGES, 'START', 'C') → ['START', 'HUB', 'C']

- If this is wrong, fix it now. A wrong graph discovered on Day 6 costs two days.

## 6.2 path_planner_node.py — Terminal Input + Route Publisher

This node presents the terminal menu, takes user input in a background thread, runs Dijkstra, and publishes the route as a nav_msgs/Path message.

| Publishes | /planned_path (nav_msgs/Path), /navigation_command (std_msgs/String) |
| --- | --- |
| User Interaction | Blocking input() in a daemon thread — non-blocking to ROS spin loop |
| On Destination Arrival | Resets and prints 'Destination reached! Select next destination:' |
| Path Format | Ordered list of PoseStamped waypoints in the 'odom' frame |
| Print Output | Prints: 'Shortest Path: START → HUB → B (40m). Navigating...' |

## 6.3 waypoint_follower.py — P-Controller Navigation

This node reads the current robot position from /odom and steers toward each waypoint in sequence using a proportional controller.

| Subscribes | /planned_path (nav_msgs/Path), /odom (nav_msgs/Odometry) |
| --- | --- |
| Publishes | /cmd_vel (geometry_msgs/Twist) — but only in NAVIGATING state |
| Control Loop Rate | 10 Hz timer callback |
| Linear Speed | Max 4.17 m/s (15 km/h), proportional to distance from waypoint |
| Angular Speed | P-gain 1.2 on heading error, capped at 1.0 rad/s |
| Waypoint Arrival Radius | 0.8 metres — advance to next waypoint |
| Turn Behaviour | If heading error > 0.3 rad, reduce linear.x to 1.0 m/s until aligned |
| Terminal State | On final waypoint reached: publish zero Twist, send DESTINATION_REACHED |

## 6.4 obstacle_detector.py — LiDAR Perception

This is the primary safety perception node. It reads /scan at 10 Hz and determines if anything is within the danger threshold.

| Subscribes | /scan (sensor_msgs/LaserScan) |
| --- | --- |
| Publishes | /obstacle_detected (std_msgs/Bool), /obstacle_direction (std_msgs/Float32) |
| Stop Threshold | 1.5 metres — Section 5.1 of implementation plan |
| Direction Computation | min_range_index × angle_increment + angle_min = obstacle bearing |
| False Positive Filter | Require 3 consecutive detections before publishing True (avoids noise spikes) |
| Clear Filter | Require 5 consecutive clear readings before publishing False (Section 5.1 resume logic) |

## 6.5 ultrasonic_monitor.py — Corner Safety Layer

This node provides the defence-in-depth layer from Section 11.1. It monitors all four corner sensors independently.

| Subscribes | /ultrasonic/front, /ultrasonic/rear, /ultrasonic/left, /ultrasonic/right |
| --- | --- |
| Publishes | /ultrasonic_alert (std_msgs/Bool) |
| Stop Threshold | 0.30 metres — Section 11.1 |
| Trigger Logic | ANY single sensor below 0.30m triggers True immediately — no filtering |
| Priority | Ultrasonic alert overrides LiDAR state — it is the hard-stop layer |

## 6.6 crowd_detector.py — Simulated Crowd Detection

Real computer vision crowd detection (YOLO) is explicitly out of scope for Phase 1. This node provides a physically meaningful LiDAR-based proxy that will be replaced by a real ML model in Phase 2.

| Subscribes | /scan (sensor_msgs/LaserScan) |
| --- | --- |
| Publishes | /crowd_detected (std_msgs/Bool) |
| Detection Logic | Count LiDAR rays with range values between 0.5m and 3.0m simultaneously |
| Threshold | If count > 40 rays → crowd detected (a crowd of people produces dense returns) |
| Tune On Day 6 | Adjust the 40-ray threshold during testing by placing obstacle clusters |
| Phase 2 Note | Will be replaced by YOLO inference on /camera/image_raw in Phase 2 |

## 6.7 state_machine.py — Master Behavioural FSM

This is the brain of the system. It runs at 10 Hz and manages all state transitions. Every other node defers to the state machine's output on /buggy_state.

| State | Entry Condition | Exit Condition |
| --- | --- | --- |
| WAITING_FOR_DESTINATION | System startup | Receives 'START' on /navigation_command |
| NAVIGATING | Destination selected | Obstacle detected OR crowd detected OR destination reached |
| EMERGENCY_STOP | /obstacle_detected = True OR /ultrasonic_alert = True | 5 consecutive clear LiDAR readings |
| RESUMING | 5 clear readings received | 1 cycle timer (0.5s safety delay) → NAVIGATING |
| CROWD_DETECTED | /crowd_detected = True | 3-second terminal countdown completes |
| MANUAL_CONTROL | Countdown completes, driver takeover announced | /manual_override = False published |
| DESTINATION_REACHED | Final waypoint within 0.8m | New destination selected via terminal |

Terminal output during CROWD_DETECTED state:

[STATE MACHINE] CROWD DETECTED — Requesting driver takeover

[SAFETY]  Handing control to driver in 3...

[SAFETY]  Handing control to driver in 2...

[SAFETY]  Handing control to driver in 1...

[SAFETY]  MANUAL_CONTROL active. Awaiting driver clearance.

## 6.8 speed_controller.py — Velocity Command Publisher

This node reads /buggy_state and publishes the appropriate /cmd_vel Twist command. It is the only node allowed to publish to /cmd_vel.

| Subscribes | /buggy_state (std_msgs/String) |
| --- | --- |
| Publishes | /cmd_vel (geometry_msgs/Twist) |
| NAVIGATING speed | Defers to waypoint_follower — reads waypoint_follower output |
| EMERGENCY_STOP speed | Immediately: linear.x = 0.0, angular.z = 0.0 |
| RESUMING speed | Ramp from 0 → 4.17 m/s over 1.0 second (smooth resume) |
| WAITING / MANUAL_CONTROL | Zero velocity always |

## 6.9 demo_visualizer.py — RViz2 Markers

This node publishes visual markers to RViz2 to make the demo immediately understandable to any viewer.

| Marker Type | What It Shows |
| --- | --- |
| Green sphere at each node | Named campus destinations: A, B, C, HUB with TEXT labels |
| Yellow LINE_STRIP | The planned path from current position to destination |
| Red sphere ahead of buggy | Location of detected nearest obstacle computed from LiDAR range + direction |
| Coloured safety rings | Green ring at 3m, Yellow ring at 1.5m, Red ring at 0.3m around buggy |

# 7. 10-Day Parallel Execution Schedule

The team of six is divided into three sub-teams that work in parallel. Integration points are fixed at end of Day 5 and end of Day 8. Each day has a non-negotiable success criterion — if it is not met, the next day's work cannot proceed safely.

## 7.1 Team Assignments

| Sub-Team | Members | Responsibility |
| --- | --- | --- |
| Team Alpha (Infrastructure) | Member 1 + Member 2 | URDF model, sensor plugins, campus world, launch files |
| Team Bravo (Intelligence) | Member 3 + Member 4 | Dijkstra graph, path planner, waypoint follower, state machine |
| Team Charlie (Safety + Demo) | Member 5 + Member 6 | Obstacle detection, ultrasonics, crowd detector, RViz2 visualizer, demo scripts |

## 7.2 Day-by-Day Schedule

| DAY 1 Team Alpha | Environment Setup + Base Vehicle Model |
| --- | --- |

GOAL: colcon build passes. Golf cart spawns in empty Gazebo world. /cmd_vel topic exists. ros2 topic list shows /odom.

- Install all ROS 2 packages from Section 2.2 — run the full apt command

- Source ROS 2 in ~/.bashrc: echo 'source /opt/ros/humble/setup.bash' >> ~/.bashrc

- Create workspace: mkdir -p ~/srm_buggy_ws/src && cd ~/srm_buggy_ws

- Search GitHub for golf cart URDF (90-minute time limit — then fall back to Husky)

- Clone best available URDF into ~/srm_buggy_ws/src/

- Run colcon build — fix dependency errors from error messages

- Launch the vehicle in empty Gazebo world — confirm it appears

- Run ros2 topic list — confirm /cmd_vel and /odom are present

- Push initial repository structure to GitHub

- Create package: ros2 pkg create --build-type ament_python buggy_brain

- Create package: ros2 pkg create --build-type ament_cmake buggy_bringup

DAY 1 SUCCESS CRITERION: 'ros2 topic pub /cmd_vel geometry_msgs/msg/Twist "{linear: {x: 1.0}}" --once' makes the buggy move forward in Gazebo. If it does not move, Day 1 has failed.

| DAY 2 Team Alpha | Sensor Plugins + Campus World |
| --- | --- |

GOAL: All five sensor topics publishing real data. Buggy sits in campus world with road network visible.

- Add eight sensor links to base XACRO using the template from Section 3.3

- Add Gazebo sensor plugins for LiDAR, camera, IMU, GPS, and four ultrasonics

- Create srm_campus.world SDF file with roads, walls, destination markers

- Create campus_world.launch.py in buggy_bringup that launches Gazebo with the world

- Create buggy_spawn.launch.py that spawns the URDF model at START position

- Run colcon build — fix XACRO syntax errors (most common: unclosed tags, wrong namespaces)

- Verify: ros2 topic echo /scan → must show ranges[] array with real values

- Verify: ros2 run rqt_image_view rqt_image_view → camera image must show road

- Verify: ros2 topic echo /ultrasonic/front → single range value updating

- Common error: ray sensor plugin not finding topic — check ros2 namespace in plugin config

DAY 2 SUCCESS CRITERION: ros2 topic list shows ALL of: /scan, /camera/image_raw, /imu/data, /gps/fix, /ultrasonic/front, /ultrasonic/rear, /ultrasonic/left, /ultrasonic/right. Run ros2 topic hz /scan and confirm 10 Hz. If any topic is missing, do not proceed to Day 3.

| DAY 3 Team Bravo | Dijkstra Graph + Path Planner + Waypoint Follower |
| --- | --- |

GOAL: User types destination in terminal → path computed → buggy starts moving toward first waypoint.

- Write map_graph.py with NODES, EDGES dictionaries and find_shortest_path() function

- TEST STANDALONE: python3 map_graph.py — print results for all destination pairs

- Write path_planner_node.py with threading.Thread for input() — daemon=True flag required

- Test path_planner_node standalone: run it, type 'B', confirm Path message printed

- Write waypoint_follower.py with P-controller, 10 Hz timer, waypoint advancement logic

- Test waypoint_follower with fake /odom: ros2 topic pub /odom ... and watch /cmd_vel output

- Add all three to setup.py entry_points and run colcon build

- Integration test: run path_planner + waypoint_follower together, type destination, confirm Twist commands appear on /cmd_vel

DAY 3 SUCCESS CRITERION: Launch path_planner_node and waypoint_follower_node. Type 'B'. Watch ros2 topic echo /cmd_vel show non-zero linear.x. In Gazebo, buggy begins moving toward B. Confirm the route passes through HUB before reaching B.

| DAY 4 Team Charlie | Obstacle Detection + State Machine + Ultrasonic Monitor |
| --- | --- |

GOAL: Place box in path → buggy stops → remove box → buggy resumes → continues to destination.

- Write obstacle_detector.py with consecutive-reading filter (3 for detect, 5 for clear)

- Write ultrasonic_monitor.py with immediate trigger on any sensor < 0.30m

- Write state_machine.py with all seven states and all transition conditions from Section 6.7

- Write speed_controller.py that reads /buggy_state and publishes appropriate /cmd_vel

- Write crowd_detector.py with ray-count threshold method

- Test each node in isolation: manually publish inputs using ros2 topic pub and verify outputs

- Test state machine transitions: pub True to /obstacle_detected → confirm /buggy_state shows EMERGENCY_STOP

- Test resume: pub 5x False to /obstacle_detected → confirm RESUMING then NAVIGATING

DAY 4 SUCCESS CRITERION: With all nodes running simultaneously: ros2 topic pub /obstacle_detected std_msgs/msg/Bool '{data: true}' --once triggers EMERGENCY_STOP within one cycle. Five False publications return to NAVIGATING. /cmd_vel shows zero during stop and 4.17 m/s during navigation.

| DAY 5 ALL TEAMS | Full System Integration — First End-to-End Run |
| --- | --- |

GOAL: Single launch command starts everything. User types destination. Buggy navigates from START to destination without human intervention.

- Create full_system.launch.py in buggy_bringup that launches ALL nodes simultaneously

- Launch order: Gazebo world → robot_state_publisher → spawn buggy → all brain nodes → RViz2

- Add use_sim_time:=True to every node launch — CRITICAL for clock synchronisation

- Fix likely issues: odometry topic namespace mismatch (check ros2 topic list for exact names)

- Fix angular overshoot: reduce P-gain to 0.8 if buggy spins in circles

- Fix waypoint miss: increase arrival radius to 1.0m if buggy oscillates around waypoint

- Verify TF tree: ros2 run tf2_tools view_frames → must show odom → base_link → sensor_links

- Run complete navigation: START → B. Time the run. Record on video.

- Run complete navigation: START → C. Confirm left turn at HUB works.

DAY 5 SUCCESS CRITERION: The buggy completes at least one full navigation from START to destination B AND one to destination C without human intervention. Acceptance: it may drift 1-2m from exact destination due to odometry error. That is documented and acceptable.

| DAY 6 ALL TEAMS | Obstacle Avoidance During Navigation + Crowd Handoff |
| --- | --- |

GOAL: Buggy stops at mid-route obstacle, resumes when cleared, triggers crowd handoff correctly.

- Place obstacle_box_1 on road between START and HUB using Gazebo Insert panel

- Launch system, type 'B', watch buggy stop at 1.5m from obstacle

- Drag obstacle off road using Gazebo GUI — watch buggy resume after 5 clear readings

- Confirm buggy continues to HUB and then to B — full route completion with obstacle

- Test crowd detection: place 6-8 small boxes in a semicircle 2m ahead of buggy

- Tune crowd_detector threshold (default 40 rays) — watch ros2 topic echo /crowd_detected

- Confirm state machine prints 3-2-1 countdown and enters MANUAL_CONTROL

- Simulate driver clearing: ros2 topic pub /manual_override std_msgs/msg/Bool '{data: false}'

- Confirm return to NAVIGATING and route completion

- Test all three destination routes with obstacles — record pass/fail for each

DAY 6 SUCCESS CRITERION: Full run with obstacle stop-and-resume + full run with crowd detection handoff, both completing successfully for destinations B and C.

| DAY 7 Team Charlie | RViz2 Polish + Terminal Dashboard + Demo Rehearsal |
| --- | --- |

GOAL: Single-screen demo ready. RViz2 shows all visual elements. Terminal dashboard clear and readable.

- Write demo_visualizer.py with MarkerArray: node spheres, path line, obstacle red dot, safety rings

- Configure RViz2: Robot Model display, LaserScan display (/scan), Camera display, MarkerArray display, Path display (/planned_path)

- Save RViz2 config as srm_buggy_demo.rviz in buggy_bringup/rviz/

- Add RViz2 launch with config file to full_system.launch.py

- Set up tmux 4-pane layout: top-left = /buggy_state, top-right = /obstacle_detected, bottom-left = /planned_path, bottom-right = free terminal for destination input

- Write run_demo.sh that: kills any existing ROS processes, sources workspace, launches full system

- Rehearse full demo script out loud three times — time each run (target: under 5 minutes)

- Write one-page README.md with traceability table, topic list, how-to-run

DAY 7 SUCCESS CRITERION: Single command './run_demo.sh' opens Gazebo + RViz2 + tmux dashboard. Demo runs end-to-end in under 5 minutes. No manual terminal commands required beyond typing the destination letter.

| DAY 8 ALL TEAMS | Stress Testing + Bug Fixing |
| --- | --- |

GOAL: 8 out of 10 consecutive runs complete without crashes or hangs.

- Run complete demo 10 times consecutively from clean terminal

- Record pass/fail matrix: system launch, destination accepted, path correct, first waypoint reached, obstacle stop, resume, crowd handoff, final destination

- Common Day 8 failures and fixes:

- Gazebo memory leak crash on 3rd-4th run: add 'pkill -f gzserver; pkill -f gzclient; sleep 2' to cleanup section of run_demo.sh

- input() thread deadlock on restart: confirm daemon=True is set on the thread

- Waypoint oscillation: add minimum forward speed of 0.3 m/s so buggy always makes progress

- TF timestamp errors: confirm use_sim_time=True on ALL nodes, not just some

| DAY 9 Team Bravo | Documentation + Traceability Matrix |
| --- | --- |

- Generate RQT graph: ros2 run rqt_graph rqt_graph → screenshot as system_graph.png

- Write full traceability matrix (see Section 8 of this document)

- Record final screen capture video of working demo — 720p minimum

- Push all code to GitHub with clean commit messages

- Write Phase 2 roadmap section in README explaining what changes for real hardware

| DAY 10 ALL TEAMS | Final HOD Demo Preparation |
| --- | --- |

- Full rehearsal with HOD-level explanation prepared for each system component

- Each team member assigned a specific component to explain during demo

- Backup: pre-record video of successful run in case of machine failure during live demo

- Print one-page traceability matrix — physical copy for HOD review

- Prepare answers for likely HOD questions: Why Dijkstra not A*? Why not Nav2? What is Phase 2?

# 8. Traceability Matrix

Every component in the simulation links back to a specific section in the SRM Implementation Plan documents. This is what makes this a legitimate Phase 1 engineering deliverable, not a tutorial copy.

| Code File / Component | Spec Section | What It Implements |
| --- | --- | --- |
| map_graph.py — NODES dict | Sec 2.2 ODD Table | Named campus destinations (Main Gate, Library, Admin Block) |
| map_graph.py — EDGES dict | Sec 2.2 | Campus road network topology |
| map_graph.py — Dijkstra | Sec 5.2 Path Planning | Shortest route computation between any two nodes |
| obstacle_detector.py — 1.5m threshold | Sec 5.1 | LiDAR-based emergency stop trigger distance |
| ultrasonic_monitor.py — 0.30m threshold | Sec 11.1 | Defence-in-depth corner proximity guard |
| state_machine.py — EMERGENCY_STOP | Sec 5.2.1 | Behavioural state machine stop transition |
| state_machine.py — RESUMING delay | Sec 5.2.1 | 5 consecutive clear reading requirement before resume |
| state_machine.py — CROWD_DETECTED | Sec 7.1 Level 3 | SAE Level 3 driver takeover handoff protocol |
| speed_controller.py — 4.17 m/s | Sec 2.2 ODD | Maximum operating speed 15 km/h |
| crowd_detector.py — 40-ray threshold | Sec 7.1 / 8.2 | Crowd detection without ML — LiDAR ray density proxy |
| lidar_link position (0.0 0.0 1.85) | Sec 3.2 Sensor Table | Livox Mid-360 roof mount position |
| camera_link position (1.2 0.0 1.20) | Sec 3.2 Sensor Table | RealSense D435i front face mount |
| Gazebo LiDAR 360 samples at 10Hz | Sec 4.1 | Practical simulation of Mid-360 scan pattern |
| buggy_brain/state_machine.py | Sec 5.2 FSM | Full behavioural state machine implementation |
| srm_campus.world — HUB at (0,0) | Sec 2.2 ODD Map | Campus road network physical geometry |

# 9. Known Pitfalls and Fixes

These are the most common failure modes experienced when building exactly this type of system. Read this section before starting each day.

| Problem | Symptom | Fix |
| --- | --- | --- |
| Clock sync failure | TF transform errors, sensor data not received | Add use_sim_time:=True to EVERY node in launch file — not just some |
| Ray sensor wrong namespace | /scan not appearing in ros2 topic list | Check plugin config: <remapping>~/out:=scan</remapping> and ros namespace is / |
| Waypoint spinning | Buggy rotates continuously without moving forward | Reduce angular P-gain from 1.2 to 0.7. Add deadband: ignore heading error < 0.05 rad |
| Waypoint oscillation | Buggy bounces back and forth near waypoint | Increase arrival radius from 0.8m to 1.2m. Add minimum linear speed 0.3 m/s |
| input() blocks ROS spin | Node freezes waiting for keyboard input | Wrap input() in threading.Thread with daemon=True. Never call input() in main thread |
| Gazebo crashes on 3rd run | gzserver killed, sim window closes | Add pkill -f gzserver && pkill -f gzclient && sleep 2 to cleanup in run_demo.sh |
| odometry drift | Buggy reaches wrong coordinates after 40m journey | Document it. Say 'GPS fusion will correct drift in Phase 2'. Do not attempt to fix. |
| colcon build fails | Missing package errors | Read error message carefully, run sudo apt install ros-humble-[missing_package] |
| URDF spawn fails | Robot not visible in Gazebo | Check that spawn_entity.py receives the correct URDF string from robot_state_publisher |
| LaserScan all zeros | /scan ranges[] all 0.0 or inf | Gazebo needs objects in the scene to return non-inf values. Add wall models to world. |

# 10. Phase 2 Roadmap — From Simulation to Physical Vehicle

Phase 1 deliberately uses simplified implementations in several areas. The following table documents exactly what changes when the real hardware is assembled in Phase 2. These honest disclaimers strengthen the Phase 1 deliverable because they demonstrate engineering awareness.

| Phase 1 (This Document) | Phase 2 (Hardware) | Change Required |
| --- | --- | --- |
| Odometry-only localisation | GPS + IMU fusion | Add robot_localization EKF package with NavSatFix + Imu fusion |
| Proportional waypoint follower | Nav2 DWB controller | Implement full costmap + DWB local planner |
| Hardcoded campus graph | Dynamic SLAM map | Add slam_toolbox for real-time mapping |
| LiDAR ray-count crowd detection | YOLO on RealSense camera | Train YOLOv8 model on pedestrian dataset, run on camera feed |
| Simulated sensor data | Physical sensor hardware | ROS 2 hardware drivers for each physical sensor |
| Terminal destination input | Tablet/web UI | Implement REST API or ROS web bridge for user interface |
| Differential drive simulation | Physical motor controllers | Integrate CAN bus or PWM motor controller ROS node |

## 10.1 What Transfers Directly from Phase 1 to Phase 2

- The state machine (state_machine.py) — runs unchanged on real hardware

- The obstacle detector threshold logic — same 1.5m rule applies to physical LiDAR

- The Dijkstra graph module — same algorithm, just needs real GPS waypoints

- The ROS 2 topic architecture — all topic names and message types are hardware-compatible

- The launch file structure — only swap Gazebo for real hardware driver launches

This is the core value of Phase 1: the software architecture is not throwaway. It is the real software, running in a simulation. Phase 2 is predominantly hardware integration, not software rewrite.

# 11. HOD Demonstration Script

This section provides a rehearsed script for the final HOD demonstration. Each team member should know their assigned section. Total demo time: 4-5 minutes.

## 11.1 Demo Flow

| Step | Action + Narration |
| --- | --- |
| 0:00 — Launch | Run './run_demo.sh'. Gazebo opens with campus world. RViz2 opens alongside. tmux dashboard visible. Say: 'This is our Phase 1 SITL simulation. The campus world has three destinations mapped to actual SRM locations.' |
| 0:30 — Explain Map | Point to RViz2 green spheres: 'These green nodes are our hardcoded campus waypoints — Main Gate, Library, Admin Block, and the central HUB. The road network matches our ODD from Section 2.2.' |
| 1:00 — Select Destination | Type 'B' in terminal. Say: 'I am selecting Library Block. Watch the Dijkstra algorithm compute the shortest path.' Point to yellow line appearing in RViz2: 'The path is: START → HUB → Library.' |
| 1:30 — Navigation Begins | Buggy starts moving. Point to LiDAR pointcloud in RViz2: 'The LiDAR is scanning 360 degrees at 10Hz. Green dots are clear space.' Point to state terminal: 'State is NAVIGATING.' |
| 2:00 — Obstacle Stop | Buggy hits obstacle box. Point to red turning points and EMERGENCY_STOP in terminal. Say: 'Obstacle detected within 1.5 metres — Section 5.1. All velocity zeroed instantly.' |
| 2:30 — Resume | Remove obstacle from Gazebo GUI. Buggy resumes after 5 clear readings. Say: 'After 5 consecutive clear LiDAR scans — Section 5.1 resume condition — the buggy enters RESUMING state.' |
| 3:00 — Crowd Detection | Show crowd cluster trigger. Say: 'When 40+ LiDAR rays return simultaneously between 0.5 and 3 metres, crowd is detected. The system requests driver takeover — this is our SAE Level 3 handoff from Section 7.1.' |
| 3:30 — Arrival | Buggy reaches Library Block. Terminal prints arrival message. Say: 'Destination reached. The buggy now waits for the next instruction.' |
| 4:00 — Q&A Pointer | Point to traceability matrix printout: 'Every threshold, every speed limit, every state transition in this code links back to a section in our implementation plan document.' |

## 11.2 Likely HOD Questions and Answers

| Question | Answer |
| --- | --- |
| Why Dijkstra and not A*? | Dijkstra guarantees optimal shortest path on our small static graph. A* adds a heuristic that only helps on large grids. For 4 nodes, Dijkstra is faster and simpler. Phase 2 will use Nav2's global planner. |
| Why not use Nav2? | Nav2 requires dynamic costmaps, SLAM integration, and AMCL localisation — that is Phase 2 work. Phase 1 scopes to a demonstrable proportional controller that proves the sensor-to-action pipeline works. |
| Is the crowd detection real? | In Phase 1, crowd detection uses a LiDAR ray density threshold — physically meaningful but not ML-based. Phase 2 will replace this with a YOLOv8 model running on the RealSense D435i camera feed. |
| Why not C++ for nodes? | Python ROS 2 nodes are functionally identical to C++ nodes in terms of the topic/subscriber architecture. For simulation where we process LaserScan data at 10Hz, Python performance is sufficient. Phase 2 perception nodes will be C++ for hardware performance. |
| Will this run on the real buggy? | The state machine, obstacle detector, and Dijkstra module transfer to real hardware unchanged. The simulation's Gazebo sensor topics are replaced by physical sensor driver topics with the same message types. The architecture is hardware-ready. |

# 12. Final Delivery Checklist

Before the HOD demo, confirm every item below is checked. This is the minimum viable delivery for a passing Phase 1 demonstration.

MINIMUM VIABLE DEMO: If the system does these 5 things, Phase 1 is a success: 1. User types destination → path computes and prints 2. Buggy moves autonomously toward destination 3. Buggy stops at obstacle and resumes when clear 4. Buggy announces arrival at destination 5. System can be relaunched and run again immediately

## 12.1 Technical Checklist

| Item | Status |
| --- | --- |
| colcon build passes with zero errors | [ ] |
| All 5 sensor topics publishing at correct Hz | [ ] |
| Gazebo campus world renders with road network | [ ] |
| Dijkstra computes correct path for all 3 destinations | [ ] |
| Buggy navigates from START to B without human input | [ ] |
| Buggy navigates from START to C without human input | [ ] |
| Emergency stop triggers at 1.5m obstacle | [ ] |
| Buggy resumes after 5 clear readings | [ ] |
| Ultrasonic alert triggers at 0.30m | [ ] |
| Crowd detection triggers with 40+ LiDAR rays | [ ] |
| MANUAL_CONTROL state entered after countdown | [ ] |
| Arrival announcement printed in terminal | [ ] |
| System accepts new destination after arrival | [ ] |
| RViz2 shows: model, pointcloud, camera feed, markers | [ ] |
| run_demo.sh launches everything in one command | [ ] |
| 8 out of 10 stress test runs pass | [ ] |
| GitHub repository pushed with README and traceability matrix | [ ] |
| RQT node graph screenshot saved | [ ] |

— END OF MASTER IMPLEMENTATION PLAN —

SRM Institute of Science and Technology | Autonomous Electric Buggy | Phase 1 SITL | March 2026